## Treatment Plan
Risk ID | Risk Statement | Treatment Option | Planned Action | Proposed Owner | Priority | Target Timeline | Target Likelihood | Target Impact | Status | Validation / Acceptance Note | Target Residual Score | Target Residual Rating
R01 | Weak or inconsistently governed access could allow unauthorized access to customer or transaction information, causing confidentiality breach, fraud exposure and loss of trust. | Mitigate | Implement role-based access, identity lifecycle controls, secure authentication/MFA, periodic access reviews and security logging. | IT/Security + Business Owners | Critical | Months 2-4 | 2 | 5 | Open | Pending validation after implementation and control testing. | 10 | High
R02 | Irregular security awareness may enable phishing or social engineering, resulting in credential compromise and unauthorized system access. | Mitigate | Formalize awareness training, phishing education, event reporting and strong authentication. | GRC/HR + IT | Critical | Months 2-3 | 2 | 4 | Open | Pending validation after implementation and control testing. | 8 | Moderate
R03 | Inconsistent supplier security checks may allow a vulnerable or poorly controlled third party to compromise NovaPay information or services. | Mitigate / Share | Tier suppliers by risk; perform due diligence; include security clauses; monitor critical suppliers and cloud services. | GRC/Procurement/IT | Critical | Months 2-4 | 2 | 5 | Open | Pending validation after implementation and control testing. | 10 | High
R04 | Without a formal asset inventory, critical assets may be unmanaged, unowned or incorrectly protected, increasing the likelihood of loss or exposure. | Mitigate | Create asset inventory; assign owners; classify information; define acceptable-use and lifecycle requirements. | IT/GRC + Asset Owners | High | Weeks 2-6 | 2 | 4 | Open | Pending validation after implementation and control testing. | 8 | Moderate
R05 | Inadequate secure-development governance may introduce exploitable defects or unauthorized code changes into the payment service. | Mitigate | Establish secure SDLC, application security requirements, secure coding, security testing and controlled changes. | Engineering + Security | Critical | Months 2-4 | 2 | 5 | Open | Pending validation after implementation and control testing. | 10 | High
R06 | Unmanaged cloud configuration or access could expose services/data or cause disruption. | Mitigate | Establish cloud security responsibilities, configuration baselines, access controls and periodic review. | Cloud/IT + Security | High | Months 2-4 | 2 | 4 | Open | Pending validation after implementation and control testing. | 8 | Moderate
R07 | Technical vulnerabilities may remain exploitable if identification and remediation are not governed consistently. | Mitigate | Implement vulnerability scanning, risk-based remediation SLAs, exception handling and tracking. | IT/Security | High | Months 2-4 | 2 | 4 | Open | Pending validation after implementation and control testing. | 8 | Moderate
R08 | Insufficient logging or monitoring could delay detection of account misuse, attacks or transaction-related anomalies. | Mitigate | Define logging standards, centralize security-relevant logs, alert on priority events and review monitoring effectiveness. | Security/IT | High | Months 2-4 | 2 | 4 | Open | Pending validation after implementation and control testing. | 8 | Moderate
R09 | Reactive security decision-making may lead to inconsistent incident assessment, escalation, containment and lessons learned. | Mitigate | Document incident roles, severity criteria, response procedures, evidence handling and lessons learned; run a tabletop exercise. | Security/GRC/Management | High | Months 2-5 | 2 | 4 | Open | Pending validation after implementation and control testing. | 8 | Moderate
R10 | A technology, supplier or cyber disruption could make digital payment services unavailable and materially affect customers and operations. | Mitigate / Share | Complete business impact analysis; define recovery objectives; test backups, continuity and supplier dependencies. | Operations/IT/Management | Critical | Months 3-5 | 2 | 5 | Open | Pending validation after implementation and control testing. | 10 | High
R11 | Failure to identify and meet applicable privacy, legal or contractual requirements could cause regulatory, contractual and reputational harm. | Mitigate | Create and maintain an Irish/EU legal and regulatory obligations register; map applicable GDPR/privacy requirements to controls; retain evidence and review compliance periodically. | GRC/Legal/Management | Critical | Months 2-5 | 2 | 5 | Open | Pending validation after implementation and control testing. | 10 | High
R12 | Excessive privileged or repository access could allow unauthorized disclosure or alteration of source code and production-related configurations. | Mitigate | Restrict privileged and source-code access; review entitlements; protect repositories; log administrative actions. | Engineering/IT/Security | High | Months 2-4 | 1 | 5 | Open | Pending validation after implementation and control testing. | 5 | Moderate

## Summary
NovaPay Solutions Ltd. - Risk Treatment Plan
Treatment actions linked to the cybersecurity risk register
Metric | Value | Portfolio Note
Total treatment actions | 12 | Treatment actions are proposed for this fictional case study. Risk reduction should only be claimed after implementation and effectiveness testing. Residual risk acceptance remains a management decision.
Open actions | 12
Critical priority | 6
Target Moderate risks | 7